## Sheet1
Republic of the Philippines BANGSAMORO AUTONOMOUS REGION IN MUSLIM MINDANAO Province of Lanao del Sur Municipality of Wao
BIDS AND AWARDS COMMITTEE
SCHEDULE OF ACTIVITIES
| PROJECT NAME | MODE OF PROCUREMENT | PRE PROCUREMENT | PRE-BID CONFERENCE | OPENING OF BIDS | POST QUALIFICATION | SOURCE OF FUND | REQUISITIONER | APPROVED BUDGET FOR THE CONTRACT
1 | SUPPLY & DELIVERY OF MATERIALS FOR THE CONSTRUCTION OF RETAINING WALL OF ACCESS ROAD TO TOURISM SITE AT BRGY. CHRISTIAN VILLAGE - 40m, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEO | P 855,600.00
2 | SUPPLY & DELIVERY OF MATERIALS FOR THE CONSTRUCTION OF 24” DRAINAGE WITH CURB AND GUTTER AT WAO PUBLIC MARKET, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEO | P 4,014,350.00
3 | SUPPLY & DELIVERY OF MATERIALS FOR THE CONCRETING OF ROAD GOING TO BRGY. HALL WITH SLOPE PROTECTION AT BRGY.KILIKILI EAST, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEO | P 1,665,750.00
4 | SUPPLY & DELIVERY OF MATERIALS FOR THE CONCRETING OF ROAD AT BRGY. KABATANGAN, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEO | P 622,900.00
5 | SUPPLY & DELIVERY OF MATERIALS FOR THE COMPLETION AND LANDSCAPING OF MUNICIPAL PLAZA AT BRGY. EASTERN, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEO | P 6,358,094.60
6 | SUPPLY & DELIVERY OF MATERIALS FOR THE CONSTRUCTION OF DAY CARE CENTERS AT BRGY. PARK AREA, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEO | P 1,072,625.00
7 | SUPPLY & DELIVERY OF MATERIALS FOR THE IMPROVEMENT OF WAO MOUNTAIN SPRING RESORT AT BRGY. BANGA, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEEDO | P 558,165.00
8 | SUPPLY & DELIVERY OF CATTLE FOR THE DEVELOPMENT OF OTOP - CATTLE DISPERSAL AT WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | CAPITAL OUTLAY | DA | P 1,350,000.00
9 | SUPPLY & DELIVERY OF MATERIALS FOR THE CONSTRUCTION OF DAY CARE CENTERS AT SAN VICENTE BRGY. PAGALONGAN, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEO | P 1,072,625.00
10 | SUPPLY & DELIVERY OF MATERIALS FOR THE CONSTRUCTION OF 1 CLASSROOM AT NORTH PARK AREA ELEMENTARY SCHOOL, BRGY. PARK AREA, WAO, LANAO DEL SUR | Public Bidding | 2026-07-21 | 2026-07-31 | 2026-08-12 | August 13- August 25, 2026 | MDF 2026 | MEO | P 1,072,625.00
| Prepared by: |  |  |  | Noted by:
| LUCELLE M. BARRION |  |  |  | BELLA S. BOBADILLA
| BAC SECRETARIAT |  |  |  | BAC CHAIRPERSON